|  |
| --- |
| Communication Plan for Emergency Department Nurse Mentorship Project |
|  |
| |  |  |  |  | | --- | --- | --- | --- | | Project Team Member/Stakeholder | Communication\*  Preferred Format | Timing | Report Prepared by | | Project Sponsor | 1)Project Status Report  --In Person  2) Project Progress Report  --Email | 1) Monthly  2) Weekly | 1)-Project Manager  2)- Project Manager | | Mentorship Coordinator | 1) Progress Report  --in person  2) Training Sessions with Nurse Builders (vendor)—In person group event  3)-Training with Laerdal Simulation (vendor)—Group Activity, in person | 1)-Twice/week  2)- Daily for six weeks (per contract)  3)- Daily for three days (per contract) | 1)- Verbal status report presented to Project Manager by Mentorship Coordinator  2)- Verbal status report to be addressed with Project Manager at routine twice per week meeting  3)- Verbal status report given to Project Manager at routine twice/week meeting | | E.D. Nurse Mentors | 1)-Progress Report  --in person  2)- Training Sessions with NurseBuilders (vendor)—in person group event | 1)- Weekly  2)- Twice per week for six weeks (two RNs per class, per day) | 1)- Verbal status report by ED Nurse Mentors given to Project Manager during weekly progress meeting  2)- Training interaction to acquire competency; progress to be shared with Project Manager at weekly meetings | | E.D. Physicians  E.D. Physicians | 1)-Plan Overview with Discussion of Expectations—in person  2)- Plan Progress Report—Email | 1)- One week preceding plan implementation  2)- Weekly | 1)- Verbalized to ED physicians by Project Manager to encourage Q&A.  2)- Formal Email composed by Project Manager addressing E.D. Physicians | | E.D. Staff Nurses (non-mentors) | 1)- Plan Overview with Discussion of Expectations—In person  2)- Plan Progress Report—In person  3)- Whiteboard-led Huddle discussion—group activity, in person | 1)- Week preceding plan implementation  2)- Weekly  3)- Weekly | 1)-Project Manager  2)-Project Manager  3)- Project Manager, in conjunction with E.D. Manager | | E.D. Manager | 1)- Collaborative planning meetings—in person  2)- Plan Progress Report—In person  3)- Whiteboard Installation Meeting—in person  4)- Training with Laerdal Simulation (vendor)  5)- Training Sessions with Nurse Builders (vendor)—in person group event | 1)- Weekly prior to plan implementation  2)- Twice per week following implementation  3)- Upon arrival (ordered)  4)- Daily for three days (per contract)  5)- Twice per week for six weeks | 1)- Led by Project Manager, with stakeholder collaboration  2)- Verbal exchange of information between Project Manager and E.D. Manager  3)- Project Manager, collaboratively with IT and Quality Manager  4)- Training interaction to acquire competency  5)-Training interaction to acquire competency | | Clinical Education Facilitator  Clinical Education Facilitator | 1)- Collaborative planning meetings—in person  2)- Training with Laerdal Simulation (vendor)  3)- Training Sessions with Nurse Builders (vendor)—in person group activity | 1)- Weekly prior to plan implementation  2)- Daily for three days (per contract)  3)- Twice per week for six weeks | 1)- Led by Project Manager  2)- Training interaction to acquire competency  3)- Training interaction to acquire competency | | Unit Clerk | 1)- Plan Overview with Discussion of Expectations—In person | 1)-Week preceding plan implementation | 1)-E.D. Manager | | Information Technology Department | 1)- Whiteboard Installation Meeting—in person  2)- Training with Laerdal Simulation (vendor)—In person group activity | 1)- Upon arrival of whiteboard  2)- Daily for three days (per contract) | 1)- Project Manager, in conjunction with E.D. Manager  2)- Training interaction to acquire competency (I.T. will provide ongoing support for simulation equipment) | | Quality Manager | 1)-Whiteboard Installation Meeting—in person | 1)-Upon arrival of whiteboard | 1)-Project Manager, in conjunction with E.D. Manager and I.T. staff | | Human Resources | 1)- Plan Overview with Discussion regarding personnel ramifications—in person | 1)-Week preceding plan implementation | 1)- Project Manager, with Mentorship Coordinator and E.D. Manager | | Risk Management | 1)- Plan Overview with Discussion of Expectations—Email, Webex if requested | 1)-Week preceding plan implementation | 1)- Project Manager, with E.D. Manager | | Marketing Department | 1)-Plan Overview with Discussion of Expectations—in person  2)- Job Fair discussion—In person  3)- Advertisement of Mentorship Training Opportunity—Email, Webex | 1)- Week preceding plan implementation  2)- Following project plan implementation  3)- Following project plan implementation | 1)-Project Manager, with assistance of E.D. Manager and Mentorship Coordinator  2)- Project Manager, E.D. Manager, and Mentorship Coordinator  3)- Project Manager, Human Resources Director | |